## Sheet1
PROJECT PLAN & TIMELINE BY WEEK
TASKS BY PHASE | ROLES | WEEKS
|  | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16 | WEEK 17 | WEEK 18
START-UP
Kick-off meeting | PM, ID, Developer | bar: WEEKS WEEK 1
Create initial plan | PM, ID | bar: WEEKS WEEK 1
Client review & revise | Client, SME, ID | bar: WEEKS WEEK 2
RESEARCH & ANALYSIS
Needs Analysis | ID | bar: WEEKS WEEK 2 to WEEKS WEEK 4
Audience Analysis | ID | bar: WEEKS WEEK 2 to WEEKS WEEK 4
Content Analysis | ID | bar: WEEKS WEEK 2 to WEEKS WEEK 4
Client review & revise | Client, SME, ID | bar: WEEKS WEEK 5
DESIGN & PROTOTYPE
Write performance objectives | ID | bar: WEEKS WEEK 5 to WEEKS WEEK 6
Organize and sequence | ID | bar: WEEKS WEEK 5 to WEEKS WEEK 6
Instructional strategies | ID | bar: WEEKS WEEK 5 to WEEKS WEEK 6
UI design | iD | bar: WEEKS WEEK 7
Prototype | iD, developer | bar: WEEKS WEEK 7
Client review & revise | Client, SME, ID | bar: WEEKS WEEK 8 to WEEKS WEEK 9
DEVELOPMENT
Write storyboards & scripts | ID | bar: WEEKS WEEK 9 to WEEKS WEEK 11
Write manuals & job aids | ID | bar: WEEKS WEEK 9 to WEEKS WEEK 11
Write test items | ID | bar: WEEKS WEEK 9 to WEEKS WEEK 11
Find media | ID | bar: WEEKS WEEK 9 to WEEKS WEEK 11
Client review & revise | Client, SME, ID | bar: WEEKS WEEK 11 to WEEKS WEEK 12
PRODUCTION
Produce graphics | iD, developer, graphic designer | bar: WEEKS WEEK 13 to WEEKS WEEK 14
Record and edit audio | iD, developer, media person | bar: WEEKS WEEK 13 to WEEKS WEEK 14
Record and edit video | iD, developer, media person | bar: WEEKS WEEK 13 to WEEKS WEEK 14
Program Alpha | iD, developer | bar: WEEKS WEEK 13 to WEEKS WEEK 15
Client review & revise | bar: WEEKS WEEK 13 to WEEKS WEEK 15
Program and QA Beta | iD, developer | bar: WEEKS WEEK 13 to WEEKS WEEK 15
Client review & revise | bar: WEEKS WEEK 13 to WEEKS WEEK 15
Program & QA Final | iD, developer | bar: WEEKS WEEK 15
Client review & revise | Client, SME, ID, developer | bar: WEEKS WEEK 15 to WEEKS WEEK 16
EVALUATION
Final QA in LMS | iD, developer | bar: WEEKS WEEK 17
Pilot Test | ID | bar: WEEKS WEEK 17
Review short-term results | ID | bar: WEEKS WEEK 18
Project debrief | Team | bar: WEEKS WEEK 18
Review long-term metrics | Client, ID