## Horizon
HORIZON PROJECT PLAN & TIMELINE BY WEEK
TASKS BY PHASE	ROLES	WEEKS
		WEEK 1	WEEK 2	WEEK 3	WEEK 4	WEEK 5	WEEK 6	WEEK 7	WEEK 8	WEEK 9	WEEK 10	WEEK 11	WEEK 12	WEEK 13	WEEK 14	WEEK 15	WEEK 16	WEEK 17	WEEK 18
START-UP
Kick-off meeting	PM, ID, Developer
Create initial plan	PM, ID
Client review & revise	Client, SME, ID
RESEARCH & ANALYSIS
Needs Analysis	ID
Audience Analysis	ID
Content Analysis	ID
Client review & revise	Client, SME, ID
DESIGN & PROTOTYPE
Write performance objectives	ID
Organize and sequence	ID
Instructional strategies	ID
UI design	iD
Prototype	iD, developer
Client review & revise	Client, SME, ID
DEVELOPMENT
Write storyboards & scripts	ID
Write manuals & job aids	ID
Write test items	ID
Find media	ID
Client review & revise	Client, SME, ID
PRODUCTION
Produce graphics	iD, developer, graphic designer
Record and edit audio	iD, developer, media person
Record and edit video	iD, developer, media person
Program Alpha	iD, developer
Client review & revise
Program and QA Beta	iD, developer
Client review & revise
Program & QA Final	iD, developer
Client review & revise	Client, SME, ID, developer
EVALUATION
Final QA in LMS	iD, developer
Pilot Test	ID
Review short-term results	ID
Project debrief	Team
Review long-term metrics	Client, ID